## AEs - detail by month (hidden)
current month
| Bribe - village official | Bribe - MM agent | Violence/crime in hh | Violence/crime in community | HH dispute | Theft/stolen money | Grave AEs | other
# AEs by type
# by reporting source
recipient
neighbor/other
# cases GD intervened
resolved
unresolved
Note on H3: Author: wife kicked out, physical harm, etc.
Note on B1: Author: to start reporting next mo

## Dashboard
End of reporting period | 2/15/2016
By country
Period | Overview | Total | Total - Ke | Total - Ug | Total - Rw | Notes
From inception - end of reporting period | Recipients enrolled i.e. cleared for transfers | 34798 | 25337 | 9461 | 0
From inception - end of reporting period | Recipients initated for transfers | 31396 | 24132 | 7264 | 0 | Transfers delayed in Uganda due to elections
From inception - end of reporting period | % recipients enrolled reporting adverse events |  | 8.288% | 11.85% | N/A | Ug numbers includes full Google campaign
As of end of reporting period | Total staff as of end of reporting period | 94 | 56 | 36 | 2
| Country Directors/Field Directors |  | 1 | 2 | 1
| Data Manager/Ops Manager |  | 0 | 1 | 1
| Admin/finance |  | 4 | 3 | 0
| Field Managers/Associate Field Managers |  | 6 | 4 | 0
| Field Officers |  | 45 | 26 | 0
Denominator
Current FY (March - Feb) | % recipients reached for follow-up (w/confirmed transfer receipt) | No. of recipients sent transfers (excluding last 2 months) | 98.51% | 99.08%
Current FY (March - Feb) | Target no. of recipients to enroll |  | 12339 | 6236
Current FY (March - Feb) | Actual recipients enrolled |  | 11489 | 6632
Current FY (March - Feb) | % recipients pending payments (> 3 months) due to reg delays | No. recipients initiated transfers | 2.451% | N/A |  | Excludes Segovia campaign because payments started in Nov
February 2016 | Target no. of recipients to enroll |  | 2469 | 1322
February 2016 | Actual recipients enrolled |  | 2311 | 2197 |  | Higher than target due to some carry-over from previous months
February 2016 | Days from census to token (for recipients who received tokens in Feb) |  | 66.6983 | N/A |  | Ug not reported b/c transfers delayed due to elections; Ke reporting on rolling campaign only (201403/201507 excluded because strictly clean-up and Rarieda because different enrollment process)
February 2016 | % recipients received LS with confirmation of prior receipt | No. recipients who received lumpsum payments | 97.77% | N/A |  | Ug not reported b/c transfers delayed due to elections
January 2016 | % refusals | No. recipients attempted for census | 40.5% | 2.6%
January 2016 | Number of staff disciplinary issues |  | 0 | 0
Reference AE's experienced by caller:
January 2016 | % calls that include report of theft | No. outbound calls made | 0.1512% | 0%
January 2016 | % calls that include report of crime | No. outbound calls made | 0% | 0%
January 2016 | % calls that include report of household conflict | No. outbound calls made | 0.2268% | 0%
January 2016 | % calls that include report of bribe payment | No. outbound calls made | 0.03781% | 0%
Reference AE's observed by caller in the community:
January 2016 | % calls that include report of domestic violence | No. outbound calls made | 1.096% | 0%
January 2016 | % calls that include report of complaints in community | No. outbound calls made | 4.802% | 0.396%