## Sheet1
Status | Name | GDID | Contact phone number(recipent only)good numbers | Alternate number | Campaign | Village | Entry type | AE type | Source | Issue | Date | Action taken | Date | Recommended next action | Action taken | Date | Recommended next action | Action taken | Date | Recommended next action | Date | Action taken | Recommended next action | Date
Done |  |  |  |  | Raireda | Rabungu B | Has not received transfer | N/A | Hotline call | was worried of transfer schedule on when to received transfer | 18/7/2013 | to lydia to inquire more a bout the recipient | 18/7/2013 | ckecked received all the transfer | no transfer | 23/7/2013 |  |  |  |  | 2013-10-10 | No more transfers shedule for joseph balla | transfers are over | 2013-10-10
Done |  |  |  |  | Google | Kowi | Complaint | N/A | Hotline call | Wife believes husband is spending transfer in secret. | 18/7/2013 | informed wife that transfers were over | 18/7/2013 | confirmed in the transfer schedule | no transfer | 21/7/2013 | [5 empty] | No more transfers shedule for joseph balla | transfers are over | 2013-10-10
Done |  |  |  |  | Raireda | Malele A | Other | N/A | Hotline call | they had domestic problem but GD money wasn't the course | 18/7/2013 | confirmed by calling if they have resolved the issue | 18/7/2013 | number not available | number not available at the moment to call later | 25/7/2013 | to call again | they have resolve the issues, confirmed by calling husband and wife. | 29/7/2013
Done |  |  |  |  | Nike | Ongoro | Adverse Event | Spouse misusing money | Hotline call | [NAME] as been living in pain and suffering, she narrated on how her husband have been mistreating her, not once but these as developed to be unhabit everytime he get drunk. | 18/7/2013 | wife to register new m-pesa number and stop sending the transfer to the husband. | 18/7/2013 | inform the [NAME] on the next transfer schedule |  | 24/7/2013 | Carolina to update transfer schedule | Updated transfer schedule, sent transfers | 15/8/08 | Please call [NAME] in 1-2 days to make sure everything is ok | 29/8/2013 |  | Everything is ok with[NAME] and she received the transfer | 30/8/2013
Done |  |  |  |  | Google | Oboch | Other | N/A | Verification survey | the recipient can not operate the phone, assistant chief is in possesion of the phone and always received transfer on behalf of the recipient. And advice him on how to spend it. | 18/7/2013 | to confirm wether the recipient as a son or daughter who can assist him | 18/7/2013 | to call neighbor to see if I can reach him | call again sometime | 22/7/2013 | call again after sometime | number not available, to visit in person | 29/7/2013 | [NAME] is comfortable to be assisted by assistant chief because he cannot operate the phone due to mental problems, his son still young cannot use the phone | 2013-01-08 | assistant chief to received the tansfer and give it to the recipient, to comfirm with wife once Gd send transfer | they received the transfer with assistance from the chief and they are ok | 30/8/2013
Done |  |  |  |  | Google | kamuga | Has not received transfer | N/A | Hotline call | he believed that he was supposed to received transfer but he asn't received any transfer | 18/7/2013 | we will work on update and send transfer after confirmation | 18/7/2013 | check in transfer schedule then confirm with him | informed the recipient on the transfer shedule | 24/7/2013 |  |  |  |  | 2013-10-10 | Have check on transfers schedules but name does not appear | the recipient was not enrolled for transfers | 2013-10-10
Done |  |  |  |  | Google | Oyango | Has not received transfer | N/A | Verification survey | the number is not working | 18/7/2013 | to call again sometime | 18/7/2013 | asked the neighbor whereabout | to call the neighbor again | 25/7/2013 | neighbor can't find him | to try to reached him sometime | 29/7/2013 | Carolina to update transfer schedule | 15/8/2013 | Recipeint is actually ineligible-- you can check the enrollment database. No action | confirm the name does not appear in database | 2013-10-10
Done |  |  |  |  | Google | Sirembe | Has not received transfer | N/A | Hotline call | He has only received 4000 shillings | 18/7/2013 | them roster indicate that the recipient received transfer recently | 18/7/2013 | Advice the recipient to charge phone and always check the balance | no transfer | 19/7/2013
Done |  |  |  |  | Google | matera | Has not received transfer | N/A | Hotline call | was complaining why GD has not send the money but receive the money yesterday | 18/7/2013 | confirmed on the transfer schedule | 18/7/2013 | reciecived all the transfers | no transfer | 20/7/2013
Done |  |  |  |  | Google | Magwar | Has not received transfer | N/A | Verification survey | already recieved the transfer (on 16/june/2013) | 18/7/2013 | to check on the transfer shedule | 18/7/2013 | inform the recipient about the status of transfer. | advice the recipient always to mind checking the m-pesa balance | 24/.7/2013
Done |  |  |  |  | Google | Magwar | Has not received transfer | N/A | Verification survey | She has only received 44000 shilling which was send in the month of feb 2013 | 18/7/2013 | to confirm on the next transfer | 18/7/2013 | inform the recipient about the next transfer | will received transfer once the records updated | 25/7/2013 | Carolina to update transfer schedule | Transfer schedule updated | 15/8/2013 | to received the next transfer in 12 december 2013 | 2013-10-10
Done |  |  |  |  | Google | Kam lag A | Other | N/A | Hotline call | was not aware wether he as received all the transfers | 18/7/2013 | check on the next transfer schedule | 18/7/2013 | call to inform the recipient that no more transfers | no transfer | 21/7/2013
Done |  |  |  |  | Google | komol | Other | N/A | Verification survey | The problem was with his phone, but has received all the transfer | 18/7/2013 | check on the trarnsfer roster | 18/7/2013 | inform the recipient a bout transfer schedule | no transfer | 20/7/2013
Done |  |  |  |  | Google | kamlag A | Has not received transfer | N/A | Verification survey | the recipient has only received 40000 that was in june 2013 | 19/7/2013 | confirmed in the next transfer schedule | 19/7/2013 | inform the recipient on status of transfer | no transfer | 22/7/2013
Done |  |  |  |  | Google | kakojo |  | N/A |  | certain a person as been pretending to be rightful recipient who has been receiving the money, but difficult to determined the right person |  | check on the transfer schedule and note details | 24/7/2013 | to confirm the issue in field visit by checking the ID's of both [NAME] | record the details of the right recipient | 25/7/2013 | the right recipient is [NAME] who has already received 40000/= the ID no. [NUMBER] Although the other hand we also have [NAME] who was enrolled and as never get any transfer phone-[NUMBER] ID [NUMBER] | Updated | 15/8/2013 | the recipient received the transfer | 2013-10-10
Done |  |  |  |  | Google | Oyango | Has not received transfer | N/A | Hotline call | she has not received any money, beside revist her for backcheck | 19/7/2013 | to work on the record and update transfer | 19/7/2013 | to check on the next transfer schedule | assure recipient that will received transfer in august | 23/7/2013 | carolina to update transfer schedule |  |  | the transfers was updated to received transfer in April 2014 | 2013-10-10
Done |  |  |  |  | Google | Kasinganda | Has not received transfer | N/A | Hotline call | worried if the next transfer willbe send to him as he was informed | 19/7/2013 | to confirmed the next tranfer schedule | 19/7/2013 | will received transfer after the records been updated | call to informed the recipient a bout the next transfer | 24/7/2013 | has been inform on the next transfer and he now Ok
Done |  |  |  |  | Raireda | Manywanda A | Has not received transfer | N/A | Hotline call | thought they had not received but actually they had gotten it all | 19/7/2013 | confirmed in the transfer schedule | 19/7/2013 | inform the recipient about the transfer | no transfer | 25/7/2013
Done
Done |  |  |  |  | Google | Oboch | Has not received transfer | N/A | Hotline call | [NAME] claim that she as only received 4000/= since then no other transfer | 22/7/2013 | check on the transfer schedule | 22/7/2013 | advice to check m-pesa balance | informed him on the next transfer | 23/7/2013 | has been inform on the next transfer schedule
Done |  |  |  |  | Google | Osumba | Has not received transfer | N/A | Hotline call | She as not received any money since last year december despite being registered and given phone | 23/7/2013 | to check on records | 23/7/2013 | confirm that this millicent is not the real one | no transfer | 25/7/2013
Done |  |  |  |  | rarieda | manyuanda A | Complaint | N/A | Hotline call | Was supposed to received 500/= and already received | 29/7/2013 |  |  |  | no transfer | 29/7/2013
Done |  |  |  |  | Google | Uyemba | Has not received transfer | N/A | Verification survey | No transfer has been send to him despite registering for m-peas | 29/7/2013 | to confirmed in transfer schedule | 29/7/2013 | carolina to update transfer schedule | Updated | 15/8/2013 | has been inform on the next transfer
Done |  |  |  |  | Google | Uyemba | Has not received transfer | N/A | Verification survey | No transfer has been send to him although in transfer schedule indicated that was suppose to receive 4310/= | 29/7/2013 | to confirmed in transfer schedule | 29/7/2013 | carolina to update transfer schedule | Updated | 15/8/2013 | has been inform on the next transfer
Done |  |  |  |  | Google | Uyemba | Has not received transfer | N/A | Verification survey | No transfer has been send to him | 29/7/2013 | to confirmed in transfer schedule | 29/7/2013 | carolina to update transfer schedule | Updated | 15/8/2013 | has been inform on the next transfer
Pending |  |  |  |  | Raireda |  | Has not received transfer |  | Verification survey | she lost the phone and not yet received transfer | 2013-05-08 | Carolina to update the transfer schedule |  |  |  | 2013-10-10 | to be inform on the next transfer
Pending |  |  |  |  | Raireda | chore | Has not received transfer | N/A | Verification survey | lost the phone plus the sim card claim has not received transfer | 2013-05-08 | To register and inform has the number. |  |  |  | 2013-10-10 | renewed the line which was already registered by his name
Done |  |  |  |  | Google | Kakojo | Complaint | N/A | Verification survey | claim she was enroled but nothing has been send to him, yet the person whom she was shairing name with as benefited | 2013-02-08 | Visited, confirmed there are two people |  | Carolina to update transfer schedule | Updated | 15/8/2013 | confirm she received the transfer
Done |  |  |  |  | Google | Ongoro | SIM change | N/A | Hotline call | the line given was blocked and he purchased another one | 2013-06-08 | buy new line and register, then send details | 2013-05-09 | She purchase another line and registered |  | 2013-10-10 | she managed to renew the line and is active
Pending | [5 empty] | chore | SIM change | N/A | Hotline call | registration problem | 2013-06-08 | buy new line and register, then send details
Pending |  |  |  |  | Nike | Wangadia | SIM change | N/A | Hotline call | registration problem | 2013-06-08 | buy new line and register, then send details
Pending | [5 empty] | Malomba | SIM change | N/A | Hotline call | registration problem | 2013-06-08 | buy new line and register, then send details
Pending |  |  |  |  | ke-201307 | kanyajer | SIM change | N/A | Hotline call | registration problem | 2013-05-08 | buy new line and register, then send details |  | see what happens when uploading
Done |  |  |  |  | ke-201307 | Kapondi A | SIM change | N/A | Hotline call | registration problem | 2013-05-08 | buy new line and register, then send details |  |  | In DB
Done |  |  |  |  | ke-201307 | uhuyi | SIM change | N/A | Hotline call | registration problem | 2013-05-08 | buy new line and register, then send details |  |  | In DB
Done |  |  |  |  | ke-201307 | uhuyi | SIM change | N/A | Hotline call | registration problem | 2013-05-08 | buy new line and register, then send details |  |  | Already updated in bc
Pending |  |  |  |  | ke-201307 | uhuyi | SIM change | N/A | Hotline call | registration problem | 2013-05-08 | buy new line and register, then send details |  |  | conflicting details- to see what happens when uploading
Done |  |  |  |  | Google | Osumba | Has not received transfer | N/A | Hotline call | claim to be enrolled by the GD, no transfer he as received | 2013-04-08 | his does not appear in the google roster was not enrolled |  | Have you checked the transfer schedule? | No transfer has been schedule for [NAME] | 2013-10-10
Done |  |  |  |  | ke-201307 | Rambo | SIM change | N/A | Hotline call | registration problem | 2013-04-08 | buy new line and register, then send details |  |  | Already updated in bc
Done |  |  |  |  | ke-201307 | kanyajer | SIM change | N/A | Hotline call | registration problem | 2013-07-08 | buy new line and register, then send details |  |  | Already updated in bc
Done |  | [NUMBER] |  |  | ke-201307 | kosema | Adverse Event | Violence | Other | the husband is very violent and does not like the idea of sending money to the wife who is our recipient, he even took the phone and kept it. | 15/8/2013 | to talk to wife secrectly if she is willing to register. And received money? |  | Carolina to find phone number and e-mail mike once she has found it. Also for [NAME] | she is willing to received the transfer and she is okey | 2013-02-08
Done |  | [NUMBER] |  |  | ke-201307 | kosema | Adverse Event | Violence | Other | the husband is very violent and does not like the idea of sending money to the wife who is our recipient, he even took the phone and kept it. | 15/8/2013 | to talk to wife secrectly if she is willing to register. And received money? |  | Carolina to find phone number and e-mail mike once she has found it. Also for [NAME] | she has register the line and she is okey | 2013-02-08
Done |  |  |  |  | ke-201307 | Nyawara B | SIM change | N/A | Hotline call | registration problem | 16/8/2013 | Changed the line |  |  | In DB
Done |  |  |  |  | ke-201307 | kosema | SIM change | N/A | Hotline call | registration problem | 22/8/2013 | Changed the line |  |  | Already updated in bc
Done |  |  |  |  | ke-201307 | Nduru upper | SIM change | N/A | Hotline call | registration problem | 22/8/2013 | Changed the line |  |  | Already updated in bc
Done |  |  |  |  | ke-201307 | Nduru upper | SIM change | N/A | Hotline call | registration problem | 22/8/2013 | Changed the line |  |  | Already updated in bc
Pending |  |  |  |  | Nike girl | wathore | Adverse Event | N/A | Hotline call |  | 23/8/2013 | to confirm from neighbor if its true and stop sending transfer
Done |  |  |  |  | ke-201307 | Angoro lieye A | SIM change | N/A | Hotline call | registration problem | 24/8/2013 | Changed the line |  |  | Already updated in phone verif
Done |  |  |  |  | ke-201307 | upanda | SIM change | N/A | Hotline call | registration problem | 30/8/2013 | Changed the line |  |  | Carolina updated
Pending |  |  |  |  | Rarieda | Ngangoe | Adverse Event | Theft | verification calls | She lost the phone, and in the process of renewing the line the Agent transfer the money to another line in order to withdraw later. | 2013-02-09 | Told them to meet with the chief |  | Mike-- please confirm that they met with the chief and things are OK | I met the chief but the investigation is still underway | 2013-02-10
Pending |  | [NUMBER] |  |  | google | BUNGU | Complaint | N/A | Hotline call | the husband claim that the wife is planning to run away with the second transfer in order to start a business in mombasa, however he used the first transfer to buy house materials and perhaps waiting for second lump sum to build the house. So he asking if GD can transfer the money to his line because he want to stand with his family. | 2013-04-09 | ? |  | confirm with both spouses | to try again to call | 2013-10-10
Done |  |  |  |  | ke-201307 | Acheo | Complaint | N/A | Hotline call | the wife claim that the husband is planning to run out of home in order to go to city to spend the money yet she is the one with children at home facing the daily challenges while the husband spend the whole day in alcohol, she want the money to be send on her line which is [NUMBER] | 2013-09-09 | I call the husband and confirm the details but disagree with the wife, the husband to remain the beneficiary | 18/9/2013
Done |  | [NUMBER] |  |  | ke-201307 | kopondi C | SIM change | N/A | Hotline call | registration problem | 18/9/2013 | changed the line |  |  | Carolina updated
Done |  |  |  |  | ke-201307 | Kapondi C | SIM change | N/A | Hotline call | regisration problem | 18/9/2013 | changed the line |  |  | Carolina updated
Done |  |  |  |  | ke-201307 | Malomba | SIM change | N/A | Hotline call | registration problem | 2013-01-10 | changed the line |  |  | Already updated in phone verif
Done |  |  |  |  | ke-201307 | uhuyi | SIM change | N/A | Hotline call | registration problem | 2013-01-10 | changed the line |  |  | Carolina updated
Done |  |  |  |  | ke-201307 | Ralak | SIM change | N/A | Hotline call | registration problem | 2013-02-10 | changed the line |  |  | Carolina updated
Done |  |  |  |  | Google | kamlag | Adverse Event | spouse misusing money | Hotline call | [NAME] was a beneficiary of GD, he received the token plus the second trasnsfer (40000) but the spouse who is [NAME] reported to us by calling the Hotline to inform us on how the husband misuses the funds by involving himself in heavy drinking of alcohol and the rest of the money he spend on marrying another wife somewhere. i call patrick to find out on how he spend the money but disagree on drinking alcohol but he marry another wife, i inform him that the next will be send to [NAME] to see if could be any impact on how she was going to spend the money, but later after the transfer was send [NAME] used part of money to open shop and buy iron sheets which they used to build a house although the money wasn't enough she was forced to borrow 5000 from her sister in order to complete the house, all this effort didn't mean anything to husband thus he went and reported wife to a police station to be arrested claiming that the wife squander the money which was not true, the policeman call GD hotline after confirming that the wife spend money properly on important issues, but late we managed to solve the differences of wife and husband. | 2013-02-10 | I call both the wife and the husband to let them know much a bout transfer | 2013-02-10
Done |  |  |  |  | ke2013007 | Nyawita | Adverse Event | N/A | backcheck survey | [NAME] happen to be married to husband who had another wife, but it happen that elder wife travel to the city for some days later to realise that the [NAME] was going to benefit from GD on her house which she used as a kitchen although this recipient was using that room as a place to sleep, this issue worsen and later the senior wife send [NAME] away, this situation forced [NAME] to go back to Kisii where her parent was but communicated to us about being in Kisii although the senior wife was staying in a permanent house and she could not meet our eligibility cretria | 2013-04-10 | to ask carolina to consinder this recipient case is legitimate. | 2013-10-10
Pending | [5 empty] | Malomba | SIM change | N/A | Hotline call | registration problem | 2013-11-10 | enter the correct number
Pending | [5 empty] | Agoro lieye | SIM change | N/A | Hotline call | registration problem | 2013-12-10 | enter the correct number
Pending | [5 empty] | Agoro lieye | SIM change | N/A | Hotline call | registration problem | 2013-12-10 | enter the correct number
Pending |  |  |  |  | ke-201307 | Nduru upper | SIM change | N/A | Hotline call | registration problem | 14/10/2013 | changed the line | 14/10/2013 | carolina to update
Pending |  |  |  |  | ke-201307 | Ralak | SIM change | N/A | Hotline call | registration problem | 14/10/2013 | changed the line | 14/10/2013 | carolina to update correct number
Done |  | [NUMBER] |  |  | ke-201307 | uchona | Adverse Event | Violence | Other | the recipient complain of threats non recipient who [NAME] that he will harm her with machette given that he was not eligible | 14/10/2013 | [NAME] who is our recipient confirm the incident but said they have already settled the issue with [NAME] with the help of village elder | 14/10/2013
Pending |  | [NUMBER] |  |  | ke-201307 | Kanyajer A | SIM change | household disagreement | Hotline call | [NAME] and [NAME] experience differences of opinion that who should receive the money from GD which eventually led to their separation, However the husband request to sustain the transfer until they can resolve their differences | 15/10/2013 | to shift their transfer forward by one and confirm later if they have resolved their issue before sending transfer | 15/10/2013
Done |  | [NUMBER] |  |  | ke-201307 | uhuyi | SIM change | N/A | Hotline call | She tried to renew the line but was not successful and end up buying another one yet the transfer was already send to this number [NUMBER] | 15/10/2013 | to reverse the money to right number [NUMBER] | 15/10/2013 |  | Had not yet sent transfer because she is pending--updated number in enrollment DB
Pending |  | [NUMBER] |  |  | ke-201307 | Sirembe | SIM change | N/A | Hotline call | the recipient unfortunate forgotten the start key in order to access her account thus forced to buy another line and register yet the transfer was already send to this [NUMBER] | 15/10/2013 | to reverse the money to right number [NUMBER] | s
Pending |  | [NUMBER] |  |  | ke-201307 | Udonga | SIM change | N/A | Hotline call | Registered with correct name but cannot access account for some reason | 17/10/2013 | reverse and send to correct number in November | 17/10/2013
Pending |  | [NUMBER] |  |  | ke-201307 | Malomba | SIM change | N/A | Verification survey | Registered with correct name but cannot access account for some reason | 18/10/2013 | reverse and send to correct number in November
Done |  | [NUMBER] |  |  | ke-201307 | Agoro lieye | Complaint | Rumor | Hotline call | [NAME] was being Accused falsely by certain non recipein,t who reported to our hotline number that she was walking in the village collecting bribe of 2000/= to each households that she tricked to be enrolled in the project. | 25/10/2013 | I made short verification calls to around 120 recipient from Agoro lieye A&B who were available on phone to confirm the accusation but non of the recipients proof [NAME] to be guilty
Pending |  |  |  |  | ke-201307 | Malomba | Adverse Event | Violence | Hotline call | [NAME} and [NAME] experience unpleasant incident after the husband allegedly acussed of foughting the wife and even sending him away simply because the wife didn't inform him that GD has send the transfer | 25/10/2013 | to shift their second transfer forward by one month and confirm later if they have resolved their differences before sending transfer
Pending |  |  |  |  | ke-201307 | uhuyi |  | Spouse misusing money | Hotline call | [NAME] reported to GD through our hotline that [NAME] who is the spouse, disappeared with the transfer immeaditely after receiving and nobody knows whereabout, | 25/10/2013 | to confirm the incident by calling if true then changed the number to the husband
Pending |  | [NUMBER] |  |  | ke-201307 | Nyambara B | Complaint | N/A | Hotline call | [NAME] reported that the spouse who is [NAME] disappear with the transfer after receiving and left children with the husband | 25/10/2013 | call to confirm the incident if true then change the number
Note on F35: GIVEDIRECTLY: k
Note on F34: GIVEDIRECTLY: ke-201307