## Dashboard
Reporting through: | 2015-08-31
[5 empty] | By year |  |  |  | By country |  |  | Completed campaigns | [7 empty] | Open campaigns | [15 empty] | Open campaigns
|  | Source |  | Total | 2012 | 2013 | 2014 | 2015 | Total - Ke | Total - Ug | Historical average | Ke-RCT | Ke-200K | Ke-Nike | Ke-Google | Ke-201307 | Ke-201311 | Ug-201305 | Ug-201404 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ke-201403 | Ug-201404 (ext) | Ug-201503
| Basic stats | [18 empty] | 05-14 | 06-14 | 07-14 | 08-14 | 09-14 | 10-14 | 11-14 | 12-14 | 1-15 | 2-15 | 3-15 | 4-15 | 5-15 | 6-15 | 7-15 | 8-15 | 8-15 | 8-15
| HHs enrolled i.e. cleared for transfers (#) | Recipient roster |  | 24943 | 1635 | 3020 | 10629 | 9659 | 20213 | 4730 |  | 498 | 199 | 77 | 861 | 2055 | 1195 | 965 | 1847 | 965 | 883 | 958 | 830 | 812 | 730 | 1030 | 1379 | 408 | 968 | 1212 | 1118 | 1066 | 1196 | 1132 | 641 | 256 | 1662
| Target HHs to enroll (#) | Workplan |  | 24593 | [7 empty] | 498 | 200 | 80 | 900 | 2000 | 1000 | 1000 | 2000 | 1000 | 1000 | 1000 | 1000 | 1000 | 539 | 629 | 1442 | 667 | 630 | 1256 | 1436 | 1256 | 641 | 908 | 908 | 153 | 1450
[12 empty] | 498 | 199 | 77 | 861 | 2055 | 1195 | 965 | 2103 | [15 empty] | 15328 |  | 1662
| HHs remaining to complete 2015 enrollment target (#) | Workplan |  | 3601
| HHs remaining to complete Q3 enrollment target (#) | Workplan |  | 1006
| Total staff (#) |  |  | 60 |  |  |  |  | 50 | 10 | [27 empty] | `
| Field Directors | HR data |  | 3 |  |  |  |  | 2 | 1
| Field/Finance Managers | HR data |  | 3 |  |  |  |  | 2 | 1
| Associate Field Managers | HR data |  | 5 |  |  |  |  | 5 | 0
| Field Officers | HR data |  | 46 |  |  |  |  | 39 | 7
| Other | HR data |  | 3 |  |  |  |  | 2 | 1
| Operational performance stats | Source | Denominator | [7 empty] | Note: shading is comparison to historical average
1. Speed | a) % recipients initiate transfer on time (Ke: 9 wks; Ug: 15 wks) | Enrollment DB/transfer sched | Recipients receiving tokens (in given month) | [5 empty] | 48.51% | 26.42% | 45.75% | Omitted | 95% | 0% | 0% | 0% | 92% | 77% | 0% | 61% | 48% | 55% | 25% | 42% | 29% | 21% | 74% | 70% | 66% | 98% | 91% | 77.13% | 55.56% | 10.8% | 0% | N/A | N/A
| b) % recipients in Ke moved through process in 30 days or less | Enrollment DB/transfer sched | Recipients receiving tokens (in given month) | [5 empty] | 21.32% | N/A | 21.32% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 40% | 11.5% | 10.37% | N/A | N/A | N/A | N/A | N/A
| c) % recipients delayed token due to registration problems | Transfer schedule | Recipients originally scheduled to received tokens (in this month) | [5 empty] | 11.27% | 9.059% | 11% | Omitted | 6% | 86% | 8% | 5% | 6% | 13% | 7% | 7% | 9% | 4% | 5% | 6% | 6% | 13% | 21% | 5% | 8% | 6% | 7% | 32.9% | 37% | 4.34% | 10.42% | N/A | N/A
| d) mean days from census to token (for recipients initiated this month) | Enrollment DB/transfer sched | N/A | [5 empty] | 71.0689 | 125.192 | 77.9088 | Omitted | Omitted | Omitted | 93.6566 | 85.75 | 62.1359 | 49 | 165 | 59 | 66 | 66 | 81 | 71 | 81 | 90 | 56.77 | 83 | 53.69 | 36 | 48 | 61.29 | 66.53 | 96.68 | 124 | N/A | N/A
2. User experience | a) % recipients reached for follow up | Follow-up data | Total receipients (as of one month before report) | [5 empty] | 95.5% | 97.9% | 95.96% | 95.81% | 99.49% | 100% | 100% | 99.32% | 99.67% | 98.02% | 99.89% | [15 empty] | 94.33% | N/A | 95.3%
| b) % score on quality audits (conducted by SFOs) | Audit data | [6 empty] | 95% | N/A | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [15 empty] | 95% | N/A | N/A
| c) % recipients feel they can transact in private | Follow-up data | Total calls | [5 empty] | 96.71% | N/A | 96.71% | Omitted | Omitted | Omitted | 91.29% | 94.92% | 96.14% | N/A | N/A | [15 empty] | 97.3% | N/A | N/A (paydays)
| d) % recipients reporting intra-hh conflict or arguments | Follow-up data | Total calls | [5 empty] | 0.4886% | 0.4463% | 0.4803% | Omitted | Omitted | Omitted | 1.858% | 0.6% | 0.19% | 1.8% | 0.07515% | [15 empty] | 0.42% | N/A | 0.13%
| e) % recipients reporting hearing about crime | Follow-up data | Total calls | [5 empty] | 0.8853% | 0.52% | 0.816% | 0.4175% | 2.02% | 1.299% | 1.51% | 0.89% | 1.5% | 2.2% | 0.16% | [15 empty] | 0.8% | N/A | 0%
| f) % recipients reporting shouting/arguments in community | Follow-up data | Total calls | [5 empty] | 1.55% | 0.7789% | 1.394% | Omitted | Omitted | Omitted | Omitted | 3.18% | 1.7% | 3.6% | 0.1% | [15 empty] | 1.32% | N/A | 0%
| g) % recipients regret spending decision | Follow-up data | Total calls | [5 empty] | 0.7279% | 0.4% | 0.7124% | Omitted | Omitted | Omitted | 0.6969% | 1.56% | 0.96% | 0.4% | N/A | [15 empty] | 0.6% | N/A | N/A
| h) % recipients did not experience improvement in life | Follow-up data | Total calls | [5 empty] | 0.5156% | 0.5013% | 0.5149% | Omitted | Omitted | Omitted | 0.2323% | 0.6% | 0.39% | 0.5013% | N/A | [15 empty] | 0.53% | N/A | N/A
3. Integrity | a) % recipients paid a bribe | Follow-up data | Total calls | [5 empty] | 0.1538% | 18.78% | 3.685% | 2.4% | 1.005% | 5.195% | 0.813% | 0% | 0% | 92% | 0.01253% | [15 empty] | 0.04% | N/A | 0%
4. Hotline performance | a) % HHs reporting AE event via hotline | Hotline | Total recipients in campaign | [5 empty] | 6.944% | 2.793% | 6.292% | 1.606% | 0% | 3.896% | 5.226% | 7.835% | 6.946% | Ommitted | 5% | [15 empty] | 7.2% | 6% | 0%
| b) % reported AE cases "closed" | Hotline | Total AEs reported | [5 empty] | 69.77% | 70.11% | 69.82% | 100% | 100% | 100% | 100% | 93.79% | 67.47% | Ommitted | 86% | [15 empty] | 63.5% | 70% | 50%
5. Staff productivity | a) avg. % target attained for census team (conditional on being in field) | Enrollment DB | Pre-determined target (35) | [31 empty] | 40% | N/A | N/A
| b) avg % target attatined for reg team (conditional on being in field) | Enrollment DB | Pre-determined target (12) | [31 empty] | 47% | N/A | N/A
| c) avg % target attatined for BC team (conditional on being in field) | Enrollment DB | Pre-determined target (12) | [31 empty] | N/A | N/A | N/A
6. Staff quality | a) # staff with documented performance issue | HR data | N/A | [17 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0

## PM note
Notes
+ Uganda 201503 campaign overshot target because drop in UGX value allowed us to enroll more recipients with previous allocation
+ Staff disciplinary issues still pending resolution (both are in Kenya, neither involve recipeint-directed fraud)
+ Time from census --> token has slowed down in Kenya for last 2 moths because HH's that were previously paused for GE study received token
+ Ke productivty for census and reg are reported from start of targeting pilot in July through end of Aug - both lower due to extension of survey for targeting pilot (note: BC step eliminated for pilot)