## Outcomes & Outputs
MENTOR WORKPLAN Yr2 - Semester 2
| Activity | Specific tasks | Semester Targets |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | Deliverables | Person/Entity in Charge | Accomplished?
| Objective 1 - Ministry of Health has sustainable integrated NTD programme across 3 provinces and capacity to scale to national coverage |  | LDA | UIG | ZAI | HBO | TOTAL | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO
Output #1 | A1.1 - Planning and Coordination Meetings at National and Provincial Level | 1- Set up regular dates for meetings in each Province with DTN Officials |  | 6 | 6 | 6 | 18 | [24 empty] | Monthly Plans at Provincial and National Levels | PM NTDP | bar: October UIG to October HBO; November UIG to November HBO; December UIG to December HBO; January UIG to January HBO; February UIG to February HBO; March UIG to March HBO
|  | 2 - Organize and put in place meetings at least once a month | [30 empty] | PM NTDP
Output #2 | A1.2 - Provide Tecnical Support for National and Provincial levels to deliver Workplans | 1 - Organize monthly meeting to writte agreed joint workplans |  | 1 | 1 | 1 | 3 | [24 empty] | Yearly Workplans Jan - Dec 2015 | PM NTDP NTDN | bar: December UIG to December HBO
| A1.3 - Provide logistical support to provincial and national NTD teams | 1 - Develop a needs assessment on logistical needs on each province |  | NA | NA | NA | NA | bar: October UIG to October HBO; November UIG to November HBO; December UIG to December HBO; January UIG to January HBO; February UIG to February HBO; March UIG to March HBO
2 - Agree on the logistical support to be given by The MENTOR Initiative both at National and Provincial levels
3 - Define a logitical support plan for the Quarter/Year
Output #3 | A1.4 - To organize regular meetings to accuratelly analyse the NTD burden data | 1 - Set up a regular meeting for data analysis in all provinces (reflected in the monthly plannings) |  | 6 | 6 | 6 | 18 | [24 empty] | Monthly NTD data table or graphic reflecting disease burden in the Province | PM NTDP | bar: October UIG to October HBO; November UIG to November HBO; December UIG to December HBO; January UIG to January HBO; February UIG to February HBO; March UIG to March HBO
|  | 2 - Design and use proper data collection and analysis tools | [30 empty] | PM NTDP NTDN
| A1.5 - Data report handing over in time | 1 - Set up a week/days in the month for this activity (reflected in the monthly planning). Should be near the deadline for monthly data collection |  | 50% of municipal health authority | 50% of municipal health authority | 50% of municipal health authority | 50% of municipal health authority | January UIG: Supervisions; January ZAI: Supervisions; January HBO: Supervisions; February UIG: Supervisions; February ZAI: Supervisions; February HBO: Supervisions; March UIG: Supervision; March ZAI: Supervision; March HBO: Supervision | Supervision forms correctly filled (used for output indicator 2.3) | PM/SUP/NTDP
2 - Conduct data collection trips in accordance to data supervisions to Municipal Health teams (A2.3)
Output #4 | A1.6 - Organize specific meetings targeting NTD drug supply for MDA and health facilities | 1 - Set up a regular monthly date with NTD, EM and MoE officials in each province (should be reflected in the monthly workplans) |  | 6 | 6 | 6 | 18 | [24 empty] | Stock balance disagregated by NTD drug/municipality with expiry dates | PM/NTDP/EM | bar: October UIG to October HBO; November UIG to November HBO; December UIG to December HBO; January UIG to January HBO; February UIG to February HBO; March UIG to March HBO
|  | 2 - Assess the current stocks and expiry dates in HF and municipal warehouses in each municipality | [30 empty] | PM/NTDP/EM
|  | 3 - Create and update on a monthly basis a NTD stock control database inarticulation with NTD and EM programs in provinces | [29 empty] | Updated stock control spreadsheet | PM/NTDP/EM
| Objective 2 - Primary Health Care System (PHC) in provinces has competency and delivers systematic NTD control |  | LDA | UIG | ZAI | HBO | TOTAL | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO
Output #1 | A2.1 - Organize training sessions of health workers on the prevention, management and reporting of NTD | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan |  | 100 | 30 | 100 | 230 | UIG: 33; ZAI: 30; HBO: 33; UIG: 33; HBO: 33; UIG: 33; HBO: 33 | Monthly workplan with trainings dates | PC/NTDP
2 - Inform Provincial and Municipal Authorities about the training dates (inform with letter)
|  | 3 - Prepare training logistics (training materials and cattering) | [29 empty] | Attendance Spreadsheet filled | PM
4 - Deliver the training
|  | 5 - Writte a Training Report | [29 empty] | Training Report | PM/NTDP
Output #2 | A.2.2 - Produce technical guidelines and disseminate to health Facility | 1 - Produce technical guidelines and get NTD Program aproval |  | 130 | 50 | 120 | 300 | UIG: 30; ZAI: 10; HBO: 20; UIG: 50; ZAI: 20; HBO: 50; UIG: 50; ZAI: 20; HBO: 50 | Set of Technical guidelines aprooved and printed | PC/NTDN
|  | 2 - Print the aprooved guidelines | [29 empty] | Guideline delivery form | PM
|  | 3 - Deliver the guidelines to Health Workers | [30 empty] | PM
Output #3 | A2.3 - Perform joint technical supervisions with Provincial NTD coordinators to municipal health departments on NTD data collection and analysis | 1 - Define a clear NTD data management system |  | 48 | 18 | 33 | 99 | UIG: 16; ZAI: 6; HBO: 11; UIG: 16; ZAI: 6; HBO: 11; UIG: 16; ZAI: 6; HBO: 11 | Data collection tools; Defined dates for report submission (na aproved NTD data calendar), NTD epidemiological database | PC/NTDN
|  | 2 - Train Provincial Supervisors on the data management sytem | [30 empty] | PM/SUP/NTDP
|  | 3 - Define a Supervision Guide for Municipal Health Teams | [29 empty] | Supervision guide | PC/NTDN
|  | 4 - Plan Monthly supevrision visits to Municipal Health Teams | [29 empty] | Supervision dates (reflected in the Monthly Plan) | PM/NTDP
|  | 5 - Conduct Regular monthly supervisions to Municipal health teams | [29 empty] | Supervision Guides Filled and data analyzed | PM/SUP/NTDP
Output #4 | A2.4 -produce and disseminate IEC techncial guidelines and education material in partnership with the national NTD Program | 1 - Produce IEC technical guidelines and get NTD Program aproval |  | 130 | 50 | 120 | 300 | UIG: 30; ZAI: 10; HBO: 20; UIG: 30; ZAI: 10; HBO: 20; UIG: 30; ZAI: 10; HBO: 20 | Aproved IEC kits/guidelines/materials | PC/NTDN
|  | 2 - Print the aprooved guidelines | [30 empty] | PC/ML
|  | 3 - Deliver the guidelines | [29 empty] | IEC delivery form | PM/SUP/NTDP
Output #5 | A2.5 - Perform technical support supervisions and coaching on NTD case management, medicine stock and supply chain management | 1 - Define a Supervision Guide for Health Units with NTDP National Program |  | 50 | 50 | 50 | 150 | UIG: 10; ZAI: 17; HBO: 17; UIG: 20; ZAI: 17; HBO: 17; UIG: 20; ZAI: 17; HBO: 17 | Health Unit Supervision Guide | PC/NTDN
|  | 2 - Train Provincial Supervisors on the use of Supervision Guide | [30 empty] | PM/SUP/NTDP
|  | 3 - Plan Monthly supervision visits to Health Units | [29 empty] | Clear dates for Supervision reflected in monthly plans | PM/NTDP
|  | 4 - Conduct Regular monthly supervisions to health units | [29 empty] | Filled Supervision guides | PM/SUP/NTDP
Objective 3 - The intensity of infection of schistosomiasis, lymphatic filariasis and intestinal worms (and potentially Onchocerciasis) in children, women and men reduced significantly from baseline. |  |  | LDA | UIG | ZAI | HBO | TOTAL | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO
Output #1 | A 3.1 - Perform mapping studies for STH and Schistosomiasis in schools | 1 - Conclude mapping |  | NA | NA | NA | 0 | [25 empty] | PM/NTDP
|  | 2 - Produce mapping reports | [29 empty] | 1 report per Province | JCF
|  | 3 - Present mapping results at Provincial and National Level | [29 empty] | 1 Provincial meeting with Municipal authorities for results presentation | PC/PM/NTDP/NTDN
Output #2 | A 3.2 - Perform mapping studies for lymphatic filariasis in communities | 1 - Get LF tests from NTD National Program |  | NA | NA | NA | 0 | [25 empty] | PC/NTDN
|  | 2 - Train the teams for LF mapping in the field | [30 empty] | PC/JCF/NTDN
|  | 3 - Conduct mapping | [30 empty] | PC/PM/SUP/NTDP
|  | 3 - Produce mapping reports | [29 empty] | 1 report per Province | JCF
|  | 4 - Present results at provincial and National level | [29 empty] | 1 Provincial meeting with Municipal authorities for results presentation | PC/PM/NTDP/NTDN
Output #3.1.3&3.2.1 | A 3.3 - Conduct MDA in schools (includes Outputs 3.1.3 & 3.2.1) | 1 - Set a MDA calendar with all necessary proceedures needed to be done in advance |  | 80% of Enrolled school age children | 80% of Enrolled school age children | 80% of Enrolled school age children | 0 | UIG: 80%; ZAI: 80%; HBO: 80% | MDA calendar (national and provincial level) | PC/PM/NTDP/NTDN
|  | 2 - Collect data on the number of existing schools/classes and children | [29 empty] | # Of schools/classes/Students per municipality | PM/NTDP/MoE
|  | 3 - Draft a distribution Plan of Medicines/Data collection tools for each Municipality | [29 empty] | Plan of Medicines distribution | PM/NTDP/EM
Output #3.1.4-3.1.7 & 3.2.2-3.2.4 & 3.3.1-3.3.2 | A 3.4 - Conduct MDA in communities (includes Outputs 3.1.4-3.1.7 & 3.2.2-3.2.4 & 3.3.1-3.3.2) | 1 - Set a MDA calendar with all necessary proceedures needed to be done in advance |  | TBD | TBD | TBD | 0 | [24 empty] | MDA calendar (national and provincial level) | PC/PM/NTDP/NTDN
|  | 2 - Collect data on the number of existing communes and population | [29 empty] | # Of communes/population per municipality | PM/NTDP
|  | 3 - Draft a distribution Plan of Medicines/Data collection tools for each Municipality | [29 empty] | Plan of Medicines distribution | PM/NTDP/EM
|  | 4 - Prepare MDA logistics (Copies/materials (Dose Poles)/funds (For trainings and Supervision) | [30 empty] | PC/NTDN/ML
Output #3.4.1 | A3.5 - Provide Annual basic NTD training to Provincial and municipal coordinators and education area coordinators | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan |  | 32 | 12 | 22 | 66 | [24 empty] | Workplan with trainings dates | PC/NTDP
|  | 2 - Inform Provincial and Municipal Authorities about the training dates (inform with letter - MoH and MoE) | [5 empty] | UIG: 32; ZAI: 12; HBO: 22 |  | PC
|  | 3 - Prepare training logistics (training materials and cattering) | [30 empty] | PC/ML
|  | 4 - Deliver the training | [29 empty] | Attendance Spreadsheet filled | PM/SUP/NTDP
Output #3.4.2 | A3.6 - Provide annual basic NTD training to teachers and school directors of MDA supported schools |  |  | 2194 | 506 | 2130 | 4830 | UIG: 2194; ZAI: 506; HBO: 2130 | Attendance Spreadsheet filled | PM/PC/NTDP
[32 empty] | Training Report | PM/NTDP
Output #3.4.2 | A3.6 - Provide annual basic NTD training to Community Drug Distributors | 1 - Plan with NTD officials (facilitators) dates for trainings. Should be reflected in the Monthly workplan |  | TBD | TBD | TBD | 0 | [24 empty] | Workplan with trainings dates | PC/NTDP
|  | 2 - Select and register CDD in each municipality | [29 empty] | List with CDD names and contacts per municipality | PC/NTDP/PM/SUP/LA/COM
|  | 3 - Inform Provincial and Municipal Authorities about the training dates (inform with letter) | [30 empty] | PC
Objective 4 - WASHE is integrated into school curriculum and hand washing with soap increased significantly from baseline |  |  | LDA | UIG | ZAI | HBO | TOTAL | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO | LDA | UIG | ZAI | HBO
Output #1 | A4.1 - Conduct a KAP study on NTD transmission and WASH Practices | 1 - Draft KAP Survey ToR |  | 0 | 0 | 0 | 0 | [24 empty] | ToR for KAP survey | MHQ
|  | 2 - Recruit a KAP survey consultant | [29 empty] | Consultant hired | MHQ
|  | 3 - KAP survey ellaboration (Survey instruments & data collectors training) | [29 empty] | Data collection tools and survey design | KAPC
|  | 4 - Conduct the KAP survey | [30 empty] | KAPC/PC/PM/SUP
|  | 5 - Deliver the KAP survey report | [29 empty] | KAP survey report | KAPC
|  | 6 - Present the survey reports at National and Provincial Levels (Output 4.1.5) | [29 empty] | 1 meeting/province | KAPC/PC/NTDP
Output #2 | A4.2 - Assess the condition and current Provision of WASHE facilities in schools in the operational area | 1 - Conduct the assessment (done with mapping) |  | 0 | 0 | 0 | 0 | [26 empty] | Yes
|  | 2 - Finalize the report | [29 empty] | Report of WASH conditions in schools | PC/JCF
Output #3 | A4.3 - Undertake hygiene information, education and communication interventions in schools targeting priority NTD | 1 - Define WASHE strategy to implement in schools |  | 0 | 0 | 0 | 0 | [25 empty] | WC
|  | 2 - Develop WASHE tools and strategies | [30 empty] | WC
|  | 3 - Develope a WASHE workplan for the 3 Provinces | [29 empty] | Workplans | WC
|  | 4 - Put in place WASHE defined strategy | [30 empty] | WC
Output #4 | A4.4 -Distribute, replenish or replace hygiene kits to all schools annually when IEC interventions are carried out | 1 - Define Hygiene kits content |  | 500 | 125 | 500 | 1125 | [24 empty] | List of items to be purchased | PC/WC/NTDN
|  | 2 - Procure Kit elements | [30 empty] | WC/ML
|  | 3 - Pack the kits | [29 empty] | Packed kits in stock | WC/ML
|  | 4 - Draft a kit distribution plan according to priorities | [29 empty] | Distribution Plan | WC/PC/PM
|  | 5 - Put in place kit distribution | [30 empty] | PM/SUP/NTDT/MoE
Output #5 | A4.5 - Provide information from all WASH assessment reports to provincial Ministry of Education officials | 1 - Organize and implement official results presentation meetings to present results |  | 0 | 0 | 0 | 0 | [24 empty] | 1 meeting/province | PC/NTDP
KEY
| PC - Program Coordinator | ML - MENTOR Logistics
| PM - Program manager | JCF - José Carlos Figueiredo
| SUP - Supervisors | DC - Data Clercks
| NTDP - NTD Provincial Programs | LA - Local Authorities
| NTDN - NTD National Program | COM - Communities
| MoE - Ministry of Education Officials | MHQ - MENTOR HQ
| EM - Essential Medicines program | KAPC - KAP consultant
WC - WASHE Coordinator