## Angola
Angola Program Management Log
Date | Event/Issue | References/Comments | DET/IPT
2015-04-02 | Feedback provided to MENTOR on Y3 documents | Revision deadline expected for Tuesday 7 April | IPT
2015-03-31 | MENTOR provides proper summary budget following request |  | IPT
2015-03-26 | Revised Y3 documents received from MENTOR |  | IPT
2015-03-25 | MENTOR contracts with Nigel Paul for Audit services | Connected by SM through past work with SCI | IPT
2015-03-15 | MENTOR confirmed deadline for revised documents as 27 March |  | IPT
2015-03-13 | Human Interest Stories Requested for DC Meeting |  | DET
2015-03-12 | MENTOR communicates to EF their intention to recruit both Onesime from Burundi MoH and Dr. Alice from the Angolan MoH | Further explanations sought out for MENTOR for rationale. The EF communicated concern given past experiences with Onesime. Approval decision pending. | IPT
2015-03-12 | Call conducted with MENTOR re: Y3 budget and workplan | MENTOR informed of EF's concern around donor funding. Need for a enhanced cost-effectiveness made clear. | IPT
2015-03-09 | Preliminary Y3 Budget received from MENTOR | Workplan still not received, budget very high without any justification | IPT
2015-03-06 | MENTOR connected with Auditor by EF and directed in EF expectations |  | IPT
2015-02-09 | DC report feedback reverted from IPT to ER |  | DET
2015-02-07 | MENTOR instructed to translate all mapping reports into English | This did have a minimal cost associated | IPT
2015-02-07 | WL, SM, MR complete Program Revision Conference from 7-14 Feb | Year 3 workplan developed. Meetings with government stakeholders completed in Luanda, Huambo and Uige. EA briefed on progress | IPT
2015-02-04 | Program Revision Meetings Agenda received |  | IPT
2015-02-01 | Feedback received from Dubai Cares | Response to be developed by 20 Feb | DET
2015-01-30 | Periodic Report Recevied | Financial report provided a few days later | IPT
2015-01-20 | Johan Willems made new country director |  | IPT
2015-01-11 | All initial UTCAH letters received for Feb field visit | Draft agenda was submitted as well | IPT
2014-12-16 | Decision to forego EF branding on purchased vehicles undertaken |  | IPT
2014-12-16 | MENTOR notified IPT by email re: transition of Country Director | Allessandro is done. | IPT
2014-12-14 | Dr. Adelaide makes commitment at JAF for Angola NTDs | WL notifies MENTOR to use as foundation for increased engagement | IPT
2014-12-12 | Wire processed and disbursement letter sent |  | IPT
2014-12-04 | Wire requested for subsquent tranche to MENTOR |  | IPT
2014-12-03 | EF approved revised PAF and Budget | Tentative approval until meetings in early February | IPT
2014-11-30 | Angola DC Report | Submitted late following breakdown in communication | DET
2014-11-26 | Subsequent funding wire received from Helmsley Trust | Enables next MENTOR disbursement | DET
2014-11-20 | Field Report Completed by SM/WL |  | IPT
2014-11-17 | MENTOR/EF Stakeholders Conference Tentatively Scheduled for First week Feb 2015 | Planned to occur in Huambo | IPT
2014-11-15 | Helmsley Trust first report submitted |  | DET
2014-11-06 | Sergio notified EF that NTD stakeholders meeting was moved up | It was moved up to next week, which precluded EF attendance | IPT
2014-11-03 | Early indications are that PZQ MDA has been successful | One minor adverse event in Uige but it was addressed w/ WHO materials | IPT
2014-11-01 | WL discussed state of ICT Kits in Angola w/ expert at ASTMH | Testing kits is not feasible, if cold chain was broken they should be binned and reordered | IPT
2014-11-01 | At COR NTD, WHO committed to mapping all of Africa (which includes Angola) by the end of 2015 | This is currently the new best guess on when LF mapping should be completed by | IPT
2014-10-30 | Quarterly report received from MENTOR |  | IPT
2014-10-24 | WL notifies MENTOR that WVI is willing to donate PZQ for <5s and adults |  | IPT
2014-10-21 | Noted that upcoming PZQ MDA includes both 3m WHO donated tabs and 3m tabs from McCleods of unknown origin |  | IPT
2014-10-21 | MENTOR undertakes to contract WASHE staff temporarily while not yet in Angola | To mitigate program delays | IPT
2014-10-20 | New census data provided on Angola | To be included in Program strategy conversation | IPT
2014-10-20 | Final STH/SCH mapping reports received for all three provinces | Program strategy to be assessed | IPT
2014-10-10 | SM and WL begin a one week and two week, respectively, field mission | Stakeholders meeting in Luanda and other meetings in provinces. Trip Report filed. | IPT
2014-10-07 | Audit Report received from MENTOR by MG |  | IPT
2014-09-29 | German instructed to send hard copy of MENTOR audit report to EF HQ | To the attention of Michael Greenberg | IPT
2014-09-25 | Ricardo confirmed his interest and intention to attend the LF mapping meeting |  | IPT
2014-09-18 | Revised JRSM form submitted by Sergio/Pedro | Correspondence between Pedro/Nzuzi and WHO | IPT
2014-09-16 | Alice notifies us that Katie Eves will be taking over Angola PM responsibilties for her | Introductory email sent to Katie | IPT
2014-09-15 | EF requested Jose to attend mapping stakeholders meeting on our behelf | And we passed along the draft agenda | IPT
2014-09-13 | Sergio provided weekly update | Touched on issues of procurement and MDA. Follow up drafted and returned a few days later. Also discussion on stakeholders meeting. | IPT
2014-09-10 | Pedro submits JRF for 2015 | Little detail, unlikely to be well-received by WHO | IPT
2014-09-10 | SM travels to Barcelona to meet with German of MENTOR | Yr2 Budget updated | IPT
2014-08-29 | Dates for field visit set | SM 12 Oct to 17/18, WL 12 Oct to 25/26 | IPT
2014-08-24 | Sergio provided weekly update | helpful briefin on current progress | IPT
2014-08-21 | German provided revised budget | Not enough/proper detail SM to follow up | IPT
2014-08-14 | Alice provided report feedback |  | IPT
2014-08-11 | Sergio provides another briefing on conversations with Pedro | Seems like he is developing rapport with Pedro | IPT
2014-08-11 | Alice writes back regarding feedback that she still needs time to collect it | Concerns about having part-time liaison at MENTOR are raised | IPT
2014-08-08 | JP Morgan Report submitted | Deadline was pushed back from 31 July | DET
2014-08-02 | Drug Donation status | WL communicated drug donation status | IPT
2014-07-31 | MR chats with Cyrille and Sergio regarding Uige APOC review | Cyrille expresses opinion on MoH NTD personnel | IPT
2014-07-31 | MENTOR submits periodic report | Feedback returned pretty promptly. | IPT
2014-07-29 | Sergio provides briefings from his conversations with Pedro | Notes perceived pressure from WHO AFRO representatives. WL shares that Onyeze approached him in Lusaka as he was checking out to talk Angola | IPT
2014-07-29 | LF Tests clear customs | Final approval still to be secured from Pedro | IPT
2014-07-25 | WHO informs us that ALB should be in country for fall MDAs |  | IPT
2014-07-22 | WL meets with Albis and Onyeze in Zambia | Challenges with Angola's application are discussed | IPT
2014-07-09 | Albis from WHO informs SM of 2014 application rejection at RPRG | Alice and Richard propose to draft a urgent plea to RPRG members as last ditch effort for 2014. MR takes up the integration of TIPAC with Alice as means of properly planning for 2015 | IPT
2014-06-27 | Push to ascertain drug donation situation begins | WL contacts WVI, SM contacts WHO, Alice follows-up SM by contacting WHO and Fenwick | IPT
2014-06-21 | WL drafts comprehensive email on meeting with Pedro | Multiple follow-up items on both LF kits and other mapping approaches. Positive meeting overall | IPT
2014-06-21 | WL reaches out to Jose Figueriedo on potential retainer as EF Angola liaison | Jose responds positively as he is now living in-country | IPT
2014-06-19 | As part of staffing email, WL requests expedited Asana adoption for Angola | Completed by 20 June, which means program log items will be increasingly stored in Asana as opposed to this sheet. This sheet will be saved for archive purposes. | IPT
2014-06-19 | Following field visit re-thinks IPT staffing responsibilities for Angola program | WL will remain hands on and travel to Angola 4x/year; SM will take lead on day to day program direction and visit Angola at least 2x/year; MR will provide more than typical time back-stopping the program as travel to Angola as requested by SM | IPT
2014-06-17 | Cyrille Evini reached out to MR to discuss his upcoming monitoring of APOC in Uige | After further conversation, Cyrille introduced to MENTOR team | IPT
2014-06-14 | WL begins field mission to Angola | Through 14 June. Trip Report completed and filed for review. | IPT
| Procurement plans at proposal stage? | Assessment of risks and challenges? WHO in-country capacity to be reliable? | LL
2014-06-03 | MENTOR informed that LF tests were still not accessed in time for Uige mapping start | Significant disappointment, WL liasing w/ WHO and Task Force to assess specific area of system breakdown | IPT
2014-05-29 | Feedback to DC submitted | Including new confirmation of reporting calendar | DET
2014-05-26 | Skype w German where little progress was shared | MENTOR continues to claim they are doing all they can | IPT
2014-05-23 | MENTOR Requested Shipping Invoice and Address information | IPT liaised with Task Force to get MENTOR the documents, no update over weekend | IPT
2014-05-22 | IPT asked MENTOR to follow up with LF Tests shipment | IPT used FedEx tracking to raise alarms, regular pestering commenced | IPT
2014-05-19 | German confirmed receipt of tranche | Approximately $1.4m | IPT
2014-05-15 | Report feedback received from DC | Responses finalized by 22 May | DET
2014-05-15 | Expedited disbursement is made to MENTOR | Follow-up conversation with MG occurs around program cash-balance. Extra funds were in UK charity | IPT
2014-05-08 | Periodic Financial Report Received | Completed using new cash-status oriented tool | IPT
2014-05-05 | WL coordinates LF test kit order with the Task Force | Turned out the kits still had not been ordered. A further conversation about how we monitor situations like this will need to occur | IPT
2014-05-01 | WL writes Richard/Alice regarding LF tests | Richard contends MENTOR moved ahead as agreed and believes WHO has it under control | IPT
2014-05-01 | MR writes Jose regarding LF tests | Jose provided some background, but had a bit of uncertainty | IPT
2014-05-01 | MENTOR submits periodic report a day late | Report subtly mentions LF tests haven't yet been ordered, fire alarms commence | IPT
2014-04-17 | Fully Execute PA sent to MENTOR | SM flagged a lack of dating the agreement | IPT
| High Risk Grant (Capacity of Mentor in NTDs, scale up capacity re: HR, and Risk of incoutry Financial Fraud possibilities) | Potential to reexamine DD especially with Grant is expanded significantly; and review of audit guidelines to be developed | LL
2014-04-10 | Partnership Agreement | EA reminded verbally on phone | IPT
2014-04-07 | Partnership Agreement | sent to Ellen for signing | IPT
2014-04-04 | briefed ellen fully on all the challenges in Angola (MOH and Mentor) | Comprehensive briefing so no surprises | IPT
2014-03-26 | MENTOR instructed to purchase ICTs and coordinate import by WHO | MENTOR commits to keep EF informed on detailed progress | IPT
2014-03-26 | Finalized DC report provided to Ellen | Following feedback from Ellen | DET
2014-03-21 | First tranche HT funding received |  | DET
2014-03-19 | First draft DC report submitted to Ellen | Date due 31 March | IPT
2014-03-19 | CNTD confirms they have line on a supply of 9,900 ICTs we can purchase | Since ICTs are made to order, processing time presented major issue to rapid procurement | IPT
2014-03-17 | WL confirms at APOC mtgs that in areas where LF/Oncho/Loa Loa are endemic - protocol is 2 rounds ALB annually |  | IPT
2014-03-17 | WL begins rapid search for ICT supply | Primary contacts are WHO AFRO and CNTD, purchase is an option w/ WHO support to import for prompt customs processing | IPT
2014-03-17 | Alice informs SM on a call that MoH did not come through with LF RDTs | WL follows up promptly with direct email to assess situation | IPT
2014-03-13 | Revised Mapping Protocol submitted from MENTOR |  | IPT
2014-02-28 | First versions of PA agreement format sent to MENTOR |  | IPT
2014-02-28 | Revised 31 Jan report received | Useful for revised PA negotiations | IPT
2014-02-27 | Mail received from Alice regarding customs issue which delayed mapping | Area of close monitoring as it is an external factor which could affect implementation going forward | IPT
2014-02-20 | Notice of HT Board approval passed along | Hooray! | DET
2014-02-13 | Positive call with HT | HT Board Mtg scheduled for 17 Feb | DET
2014-02-03 | Quarterly financial report received | First expenditure report in 6 mos | IPT
2014-01-31 | MENTOR submitted quarterly report |  | IPT
2014-01-22 | Helmsley Trust Full proposal submission through online portal |  | DET
2014-01-21 | MENTOR informally passed along treatment numbers in 2013 MDA | 567,291 treated in three provinces | IPT
2014-01-17 | Positive feedback received from Helmsley Trust | Invitation to submit through online portal | DET
2014-01-10 | First full proposal submission to Angela |  | DET
2014-01-06 | WL/SM conduct deep dive with MENTOR in UK |  | IPT
2013-12-16 | HT released full proposal template | first submission due early January | DET
2013-12-02 | LOI submitted to HT | Detailed Proposal expected 6 Dec from MENTOR | DET
2013-11-18 | Funding Envelope Provided to MENTOR | EA requested $100k from Legatum per HT year being kept in the envelope | IPT
2013-11-13 | Following call w/ HT, LOI and proposal greenlighted for mid-december | Full community based program in 3 original provinces | DET
2013-10-25 | WASHE Piece to EA for Helmsley |  | DET
2013-10-24 | Various responses and Matrix to EA for Helmsley | there does not now seem to be a clear timeline on Helmsley submission | DET
2013-10-18 | Mentor bank account details to EA for BH donation | EF owes Mentor Due Diligence infor before donation made - see email to EA | DET
2013-10-18 | Teleconference with Mentor in Angola incl RA re mapping | mapping delayed until feb 2014 - instead MOH has requested suport for MDA for incountry ALB and PZQ - EF approved | IPT
2013-10-18 | Email drafted by WL and sent to Richard to discuss mapping situation |  | IPT
2013-10-18 | Jose submits email briefing of some of this concerns on mapping |  | IPT
2013-10-18 | Internal conversations around potential mapping delays occur | Monitoring of tensions between MENTOR and Jose | IPT
2013-10-17 | Follow on conversation around matrix occurs |  | IPT
2013-10-11 | Matrix finalized and sent to EA |  | IPT
2013-10-07 | HT requests a Matrix of options to be completed by the end of the week |  | IPT
2013-10-06 | Finalized documents for Bie/WASH expansion received and processed | DC template revised. | IPT
2013-10-03 | Population estimates come from MENTOR for estimating adult treatment costs |  | IPT
2013-10-02 | In reviewing HT proposal documents, it is discovered that EF overhead limit set at 10% |  | DET
2013-10-02 | Alice provides draft budget and promises to follow up with Basile re: Bie/WASH narrative update |  | IPT
2013-10-01 | Research and conversation starts on community based treatment to include adults | Call with MENTOR occurs, research and estimates developed for EA call on 7 Oct | IPT
2013-10-01 | WL informed that new HT deadline is 30 Oct |  | IPT
2013-10-01 | WL finds out at mtgs in Uganda that Angola submitted a drug donation application. | Application poorly completed. Will need to be resubmitted | IPT
2013-09-30 | EA receives notice that HT will not be able to submit at first board meeting | EA also received request to understand potential of adult treatment | DET
2013-09-27 | EA informs team that Helmsley is delayed on things | Not telling MENTOR straightaway to keep them working | DET
2013-09-20 | Revised budget received inclusive of Bie province |  | IPT
2013-09-19 | Emails sent back and forth discussing issues within the proposal and logframe |  | IPT
2013-09-17 | Jose informs that there is no chance Angola will be mapped in 2013 | Warren to follow up informally with Richard | IPT
2013-09-13 | First revised proposal and logframe received from MENTOR | for Helmsley Trust | IPT
2013-09-11 | Budget provided to Helmsley was reviewed by Warren/Mark | It is apparent that differences in initial budget and proposal budget will need to be explained | IPT
2013-09-11 | MENTOR completes rapid assessment of NTD situation in Bie | To prepare for Helmsley Trust proposal process | IPT
2013-08-30 | EA submits report to DC | note - deadline was 29 Aug | DET
2013-08-24 | Dubai Cares report submitted to Ellen |  | IPT
2013-08-08 | EF is notified of HT's timeline postponement | MENTOR informed immediately | DET
2013-08-01 | MENTOR submits quarterly report |  | IPT
2013-07-18 | MENTOR informed about HT potential funding and requested to develop expansion plans | Timeline prepared to be ready for 6 Sept proposal template issue | IPT
2013-07-17 | EA informs EF that the Helmsley Trust has responded positively to our concept note | IPT prepares for full proposal submission in early Sept | DET
2013-07-16 | Yousuf at DC approves moving semi-annual report deadline to 29 Aug | To give IPT chance to get MENTOR's first report | DET
2013-07-03 | Angola MOU Revision Fully Executed | Wire request was provided to Charity Admin Immediately | IPT
2013-06-19 | MOU Revision submitted to Ellen for review |  | IPT
2013-06-17 | MENTOR signed MOU reivision |  | IPT
2013-06-13 | MOU modification drafted and sent to MENTOR for review | To add funding for mapping | IPT
2013-06-11 | IPT requested mapping plans status | MENTOR updated next day | IPT
2013-06-05 | Positive feedback received from Helmsley Trust |  | DET
2013-05-22 | HT concept note finalised | IPT provided last minute content during Lessons Learned | DET
2013-05-16 | IPT introduces Jose and MENTOR |  | IPT
2013-05-16 | IPT conducts call with MENTOR regarding mapping initiative |  | IPT
2013-05-14 | Further revisions were requested to HT proposal | To be discussed during EF Lessons Learned | IPT
2013-05-10 | IPT contacted Jose regarding mapping in Angola | Jose responded with interest in providing TA for activities | IPT
2013-05-08 | MENTOR notified IPT of new population estimates for Bie | DET was notified and HT proposal was modified | IPT
2013-05-08 | IPT notified that MENTOR received approval of mapping activities from MoH |  | IPT
2013-05-07 | IPT received confirmation of mapping funds | MENTOR was notified and told to begin preparing | DET
2013-05-07 | IPT informed nothing more was needed for HT |  | IPT
2013-05-03 | Helmsley Trust Concept Note Submitted to EA |  | IPT
2013-05-01 | Call with MENTOR to request information for HT proposal |  | IPT
2013-04-25 | Angola concept note for Helmsley Trust was requested |  | DET
2013-04-08 | Elisa prepared an Angola concept note for GGI consulting team | To be used in BMGF private donor engagement | DET
2013-04-02 | AM Approved MOU | Wire request was provided to Charity Admin Immediately | IPT
2013-03-26 | EA Signed MOU | EA requested Charity Admin to request AM's approval | IPT
2013-03-19 | MENTOR returned signed MOU |  | IPT
2013-03-05 | WL Followed up with WHO re: Angola Mapping |  | IPT
2013-03-04 | Revised MOU Draft was created |  | IPT
2013-02-27 | Confirmation of DC Funding was received |  | DET
2013-02-20 | Positive call with DC, decision expected by Saturday | GMT Provided an updated budget with analysis section and DC allocation | IPT
2013-02-12 | Received word that Beau and Yousuf were traveling, would circle back with feedback upon return | News expected for next week | DET
2013-01-28 | Report and Revised Proposal Submitted to DC | Full report and full revised proposal completed by GMT | DET
2012-12-12 | MENTOR requested to go ahead with hiring program manager | ultimately this was declined as DC funding looked to possibly be off the table and MOU was not able to be agreed | IPT
2012-12-07 | MENTOR DD was approved |  | IPT
2012-12-06 | Dubai Cares returns feedback that beneficiary numbers are unacceptable if not hitting 1 million SAC |  | DET
2012-11-08 | Revised proposal is provided to DC in advance of board meeting |  | DET
2012-11-05 | Dubai Cares returns with a number of questions, requests an amended proposal |  | DET
2012-10-31 | Updated Proposal Submitted to Dubai Cares |  | DET
2012-10-14 | Proposal Received from Mentor | Upon first glance, proposal appears detailed and should facilitate the review process going forward | IPT
2012-09-23 | Mentor to submit program by end of October | Start program by end of the year. | IPT
2012-09-15 | ltr from Ellen to MoH regarding fund levels, lower than expected | Reduced level of engagement by END Fund due to lower than anticipated funds available | IPT
| Mentor Initiative able to work with smaller amounts in two to three northern provinces | With reduced funding, NTD to be integrated into existing Malaria programing, school based deworming | IPT
| Decision to downsize the Angola based on available funding?? | Reference to worksheet prepared by Karen 7th September… | DET
| Report IAB dated 15 July | Option of USAID funding for mapping | IPT
| Bids received by IPs, analysis made | July 19th Preference to World Vision at that stage | IPT
July – September 2012 | Report to DC July 22 | See report attached | IPT
| Drugs have been procured by Gov’t | Availability of these drug stocks to the END Fund programs has not been confirmed | IPT
| Second official trip (Warren, Ellen, Yousuf) | Actually 3rd trip. 19-22 June | IPT
| IP identified, Bid package sent |  | IPT
| Official invitation by Government dated 14 May? |  | IPT
April – June 2012 | First official trip by END Fund | 6-19 May Report available (much progress made) | IPT
2012-04-15 | First report to IAB on Angola |  | IPT
| No responses from GoA. |  | IPT
| Official request made to Govt of Angola for engagement 15 March | Letter from Warren | IPT
January – March 2012 | February Field Visit by José | Report available | IPT
2011-12-31 | USD 1,000,000 Banked from DC for Angola |  | DET
Proposal submitted to DC | Start date project for April 2012 | Optimistic assumptions made about implementing context, Government engagement | IPT
| Assumptions made about funding levels for Angola | Optimistic assumptions made about funding levels | IPT
| Decision to apply to DC for funding |  | DET
October – December 2011 | Decision to focus on Angola | Focus made on Angola prior to anyone’s field experience. | DET