## RCT Timeline
| Treatment Group | Control Group | Scenario of Enrollment Early in Pregnancy (Month 3) Beginning of Enrollment - March | Scenario of Enrollment Early in Pregnancy (Month 3) End of Enrollment - September | Scenario of Enrollment Late in Pregnancy (Month 8) Beginning of Enrollment - March | Scenario of Enrollment Late in Pregnancy (Month 8) End of Enrollment - September | Project Timeline
2015-01-01 | Pilot | Pilot |  |  |  |  | Conduct pilot at X hospital [name redacted] ; Researcher Visits Uyo (Trip 1 of 2)
2015-02-01 | [6 empty] | Elections
2015-03-01 | 21.6667 | 21.6667 | March Enrollment in Month 3 Pregnancy |  | Enrollment in Month 8 Pregnancy |  | Second week train all clinics week of 03/9; start RCT 03/16
2015-04-01 | 43.3333 | 43.3333 | Month 4 |  | Month 9 |  | Recruit two enumerators
2015-05-01 | 43.3333 | 43.3333 | Month 5 |  | 4 Weeks Post Delivery |  | Train enumerators; Researcher has sessions with enumerator
2015-06-01 | 43.3333 | 43.3333 | Month 6 |  | 8 Weeks Post Delivery: March Enrollment Endline & EID Test |  | Endline survey begins; Researcher Visits Uyo (Trip 2 of 2)
2015-07-01 | 43.3333 | 43.3333 | Month 7
2015-08-01 | 43.3333 | 43.3333 | Month 8 |  | March Enrollment EID Result
2015-09-01 | 21.6667 | 21.6667 | Month 9 | September Enrollment in Month 3 Pregnancy |  | Enrollment in Month 8 Pregnancy | Enrollment completed
2015-10-01 |  |  | 4 Weeks Post Delivery | Month 4 |  | Month 9
2015-11-01 |  |  | 8 Weeks Post Delivery: March Enrollment Endline & EID Test | Month 5 |  | 4 Weeks Post Delivery
2015-12-01 |  |  |  | Month 6 |  | 8 Weeks Post Delivery: September Enrollment Endline & EID Test
2016-01-01 |  |  | March Enrollment EID Result | Month 7
2016-02-01 |  |  |  | Month 8 |  | September Enrollment EID Result
2016-03-01 |  |  |  | Month 9 |  |  | Midline results from RCT
2016-04-01 |  |  |  | 4 Weeks Post Delivery |  |  | First draft of publication focused on ARV pickups and delivery
2016-05-01 |  |  |  | 8 Weeks Post Delivery: September Enrollment Endline & EID Test |  |  | Endline survey completed
2016-06-01
2016-07-01 |  |  |  | September Enrollment EID Result
2016-08-01 | [6 empty] | Final draft of publication focused on HIV status of newborns
2016-09-01 | [6 empty] | Review by experts, data quality checking, secure publication sources
2016-10-16 | [6 empty] | Publish study
2016-11-16 | [6 empty] | Presentation of study in Abuja to FMOH, SURE-P, and foreign donors
2016-12-01
Totals | 260 | 260